## READ ME
BSAVA — Fonteva to NPC — Automation Inventory & Sign-off
Purpose | Row-level validation and customer sign-off of every automation in the old org (NPSP + Fonteva). Each tab mirrors a section of the 'Automation Migration Inventory & Phasing v1.0' Google Doc.
How to use | For every row: BSAVA reviews 'What it does today', confirms or overrides the Keep/Ignore recommendation, and adds comments in the 'BSAVA comments' column. Cirrico responds in 'Cirrico comments'. A row is signed off when Keep/Ignore is agreed by both parties.
Keep / Ignore values | Keep = rebuild in NPC (per the re-implementation column). Ignore = do not rebuild (reason in comments). TBC = needs a design decision or customer confirmation first.
Estimate (days) | Indicative BUILD + UNIT TEST effort for one consultant, in days. Excludes: design workshops, email template content, data migration, UAT, deployment. Rows marked 0 have no build (Ignore / covered elsewhere). Phase 3 estimates assume a Salesforce-based events solution.
Tabs | 4.1-4.6 = Phase 1 (core membership go-live) · 5 = Phase 2 (payments, finance & DD) · 6 = Phase 3 (events, CPD & LMS) · 7 = Phase 4 (committees, volunteers & certifications) · 8 = recommended exclusions, please confirm.
Key dependencies (from the doc, Section 3) | D1 email platform · D2 entitlements-to-SSO design · D3 renewal engine · D4 payment/checkout solution · D5 NPC-to-Sage path · D6 live-org capture (CRONs, templates, credentials, Badge Workflow rules).
Object mapping | Subscription->Membership__c · Renewal->Membership_Term__c · Zen_Membership_Benefit->Membership_Benefit__c · Badge/Badge_Type->Entitlement__c/Entitlement_Type__c · Sales Order/Line->Order/OrderItem · Item->Product2+Pricebook.
Source | bsavaoldprod metadata snapshot (force-app). Verified: 100 flows, 7 triggers, 23 DLRS rollups, 2 validation rules, 5 custom settings.
Companion docs | Automation Migration Inventory & Phasing v1.0 (Google Doc) · Core Data Model One-Pager v1.3 · Field Mapping workbook · Legacy Logic & Integration Reference.
Version | v1.0 · 07/07/2026 · Owner: Cirrico · Commercial in Confidence

## 4.1 Joining & Applications
4.1 Joining & Applications — Phase 1 — Core Membership go-live
# | Automation (API name) | Label (as shown in Setup) | Automation type | What it does today | NPC re-implementation | Estimate (days) | Keep / Ignore (Cirrico rec.) | Layer (Cirrico rec.) | Cirrico comments | BSAVA Reviewed | BSAVA - Keep / Ignore | BSAVA - Layer Decision | BSAVA comments
1 | Screen_Flow_Join_Process | Screen Flow - Join Process | Screen flow (11 screens) | Main membership join wizard: picks membership type and plan, captures application and referral data, builds the sales order. | Rebuild against Product2/Pricebook (types & pricing), Order/OrderItem and Membership__c. |  | TBC | UX | Anchor journey for go-live. Consolidate shared logic with the CV wizard. | No | TBC | TBC
2 | Sub_Flow_Membership_Types_to_display | Sub Flow - Membership Types to display | Autolaunched subflow | Returns the membership types to display in the join screens. | Product2 query subflow (active membership-category Products). |  | TBC | UX |  | No | TBC | TBC
3 | Sub_Flow_Subscription_Plans_to_display | Sub Flow - Subscription Plans to display | Autolaunched subflow | Returns the subscription plans/prices to display. | PricebookEntry query subflow (price per payment-method pricebook). |  | TBC | UX |  | No | TBC | TBC
4 | Sub_Flow_Member_Application_Form | Sub Flow - Member Application Form | Screen subflow | Reusable member application form incl. referral capture. | Rebuild as reusable screen subflow on the new application data. |  | TBC | UX |  | No | TBC | TBC
5 | Screen_Flow_CV_Join_Process | Screen Flow - CV Join Process | Screen flow | CV member join wizard variant. | Rebuild alongside the main wizard on the same NPC objects. |  | TBC | UX | Confirm the CV journey is still required. | No | TBC | TBC | CVS (major employer) journey
6 | CVFindSubscriptionSubFlow | CVFindSubscriptionSubFlow | Autolaunched subflow | Finds the member's current subscription for the CV join process. | Membership__c lookup subflow. |  | TBC | UX |  | No | TBC | TBC | CVS (major employer) journey
7 | CVSApplicationSubflow | CVSUpdateContactSubflow | Screen subflow | Collects CV application / address data. | Rebuild as screen subflow. |  | TBC | UX |  | No | TBC | TBC | CVS (major employer) journey
8 | CV_Sales_Order_Subflow | CV Sales Order Subflow | Autolaunched subflow | Builds the sales order for the CV join process. | Order + OrderItem creation subflow. |  | TBC | UX |  | No | TBC | TBC | CVS (major employer) journey
9 | Application_After_Save_Update | Application - After Save - Update | Record-triggered flow (Zen_Application__c) | On application approval: sends type-specific welcome emails, creates Badge, Task and Volunteer, updates the Subscription. | Record-triggered flow on the new application/Order object: welcome comms (D1), Entitlement__c creation, Membership__c update. Volunteer creation deferred to Phase 4. | 2 | Keep | Logic | Depends on D1 (email platform). | No | TBC | TBC
10 | Sales_Order_Autolaunched_Welcome_Email1 | Sales Order - Autolaunched - Welcome Email | Launched flow | Sends the correct welcome email per membership type (Full, FYQ, Nurse, Overseas, Student, 2/3YQ variants). | Flow on Order activation / Membership creation; templates rebuilt on the chosen email platform. | 2 | Keep | Logic | Depends on D1. ~8 template variants to rebuild (template effort excluded). | No | TBC | TBC
11 | selfRegister | selfRegister | Screen flow | Experience Cloud community self-registration. | Rebuild only if an Experience Cloud community is part of the NPC portal design. |  | TBC | UX | Depends on D2 (SSO/portal architecture). | No | TBC | TBC
12 | RCVS_Number_Validation (Contact) |  | Validation rule | Requires the RCVS (vet registration) number for Full / 1st-3rd Year Qualified / Postgraduate / PG Cert / Senior / Retired membership types. | Recreate on Person Account/Contact, keyed to the Product2 membership category of the active Membership__c. | 0.5 | Keep | UX | One of only 2 validation rules in the org. | No | TBC | TBC
13 | App_Trial | App Trial | Screen flow | BSAVA App free-trial signup using invitation source codes. | Rebuild the trial as a time-limited Entitlement__c. |  | TBC | UX |  | No | TBC | TBC
14 | App_Trial_Lapse_Emails | App Trial; App Trial - Lapse Emails | Scheduled flow (daily 10:00) | 10/25/31-day trial-lapse email cadence driven by Task records. | Scheduled flow on Entitlement__c expiry with the lapse cadence (drop the Task mechanism). | 1.5 | Keep | Logic | Depends on D1. | No | TBC | TBC
[5 empty] | Total (days) | 6

## 4.2 Renewals
4.2 Renewals — Phase 1 — Core Membership go-live
# | Automation (API name) | Label (as shown in Setup) | Automation type | What it does today | NPC re-implementation | Estimate (days) | Keep / Ignore (Cirrico rec.) | Layer | Cirrico comments | BSAVA Reviewed | BSAVA - Keep / Ignore | BSAVA - Layer Decision | BSAVA comments
1 | Fonteva renewal engine (SubscriptionBatchable) |  | Managed-package batch (invisible) | Generates renewal terms and renewal sales orders as memberships approach expiry (Registry config, batch size 20). | D3 — the biggest single build item. Scheduled flow/Apex on Membership__c: create the next Membership_Term__c + renewal Order at the configured lead time. | 8 | Keep | Logic | Behaviour must be specified from the live org — not visible in metadata. | No | TBC | TBC
2 | Send_Renewal_Reminder_Email | Send Renewal Reminder Email | Record-triggered flow (Task) | Sends transactional renewal reminder emails (wbsendit SendSmartEmail) when reminder Tasks are created. | Scheduled flow over Membership_Term__c expiry dates with a staged reminder cadence. | 2 | Keep | Logic | Re-specify reminder stages with BSAVA; don't copy the Task mechanism. Depends on D1. | No | TBC | TBC
3 | Screen_Flow_Sales_Order_Renewal_Form | Screen Flow - Sales Order - Renewal Form | Screen flow | Staff-side renewal order form. | Screen flow creating a renewal Order + Membership_Term__c. | 2 | Keep | Logic |  | No | TBC | TBC
4 | Sales_Order_Scheduled_Void_Old_Orders | Sales Order - Scheduled - Void Old Orders | Scheduled flow (daily) | Voids old unpaid renewal orders after a grace period (Days_till_Void). | Scheduled flow on Order (renewal flag); also lapse the Membership__c per the agreed status model. | 1.5 | Keep | Logic |  | No | TBC | TBC
5 | Cancel_Expired_Proformas | Cancel Expired Proformas | Scheduled flow (daily) | Voids/cancels expired proforma sales orders. | Scheduled flow on Order. Standard Order has no native Cancelled status — use the custom flag per the picklist mapping. | 1 | Keep | Logic |  | No | TBC | TBC
[5 empty] | Total (days) | 14.5 |  |  |  | No | TBC | TBC
[10 empty] | No | TBC | TBC
[10 empty] | No | TBC | TBC
[10 empty] | No | TBC | TBC
[10 empty] | No | TBC | TBC
[10 empty] | No | TBC | TBC
[10 empty] | No | TBC | TBC
[10 empty] | No | TBC | TBC
[10 empty] | No | TBC | TBC

## 4.3 Benefits
4.3 Benefits — Phase 1 — Core Membership go-live
# | Automation (API name) | Label (as shown in Setup) | Automation type | What it does today | NPC re-implementation | Estimate (days) | Keep / Ignore (Cirrico rec.) | Layer | Cirrico comments | BSAVA Reviewed | BSAVA - Keep / Ignore | BSAVA - Layer Decision | BSAVA comments
1 | Term_Scheduled_Loyalty_Gift_Benefits | Term - Scheduled - Loyalty Gift / Benefits | Scheduled flow (daily) | For each active unprocessed Term: picks the Formulary edition by membership category, decides loyalty-gift eligibility (renewing members only; this-year vs next-year by price rule), dedupes vs the prior term, creates the Membership Benefit. | Scheduled/record-triggered flow on Membership_Term__c (guarded by a Benefit_Calculated flag) creating Membership_Benefit__c. Formulary editions in custom metadata / migrated Formulary setting. | 3 | Keep | Logic | Full rule detail in the Legacy Logic & Integration Reference doc, Section B. | No | TBC | TBC
2 | Member_Benefit_After_Save_Create_Update | Member Benefit - After Save - Create/Update | Record-triggered flow | Stamps Contact.Zen_Current_Formulary_Owned__c from the benefit so the next term doesn't re-issue the same Formulary. | Record-triggered flow on Membership_Benefit__c stamping the equivalent field on the Person Account. | 0.5 | Keep | Logic |  | No | TBC | TBC
[5 empty] | Total (days) | 3.5 |  |  |  | No | TBC | TBC
[10 empty] | No | TBC | TBC
[10 empty] | No | TBC | TBC
[10 empty] | No | TBC | TBC
[10 empty] | No | TBC | TBC
[10 empty] | No | TBC | TBC
[10 empty] | No | TBC | TBC
[10 empty] | No | TBC | TBC
[10 empty] | No | TBC | TBC
[10 empty] | No | TBC | TBC
[10 empty] | No | TBC | TBC
[10 empty] | No | TBC | TBC

## 4.4 Entitlements & SSO
4.4 Entitlements & SSO — Phase 1 — Core Membership go-live
# | Automation (API name) | Label (as shown in Setup) | Automation type | What it does today | NPC re-implementation | Estimate (days) | Keep / Ignore (Cirrico rec.) | Layer | Cirrico comments | BSAVA Reviewed | BSAVA - Keep / Ignore | BSAVA - Layer Decision | BSAVA comments
1 | Fonteva Badge Workflow rules (OrderApi__Badge_Workflow__c) |  | Managed-package rules engine (invisible) | Paid/activated membership order line -> creates the right Badge (by Badge Type, buyer vs assigned seats, auto-expire). One new badge per term; older ones auto-expire. | Flow: when a Membership/Term becomes Active, create the right Entitlement__c from the Entitlement_Type__c linked to the Product. Export the live Badge Workflow rules first (D6). | 4 | Keep | Logic | 32 badge types in production. | No | TBC | TBC
2 | Badge_Before_Save_Create | Badge - Before Save - Create | Record-triggered flow (before save) | Sets badge expiry defaults and the Library-pass handling on new badges. | Before-save flow on Entitlement__c (expiry defaults, library-pass path). | 1 | Keep | Logic |  | No | TBC | TBC
3 | Update_User_Badge | Update User Badge | Record-triggered flow | Flattens the member's ACTIVE badges onto the community User (Badge_Ids__c, Badges__c) — what SSO/authorisation reads. | The 'active entitlements -> SSO' sync; shape depends on D2 (User fields, API, or event to Timberyard/UXL). |  | TBC | UX | Blocked by D2. | No | TBC | TBC
4 | zen_BatchUpdateUserBadges |  | Batch Apex | Nightly reconciliation of active badges onto Users. | Nightly reconciliation job (batch flow or Apex) matching the D2 design. |  | TBC | UX | Blocked by D2. | No | TBC | TBC
5 | Subscription_Before_Save_Hide_certs_in_portal | Subscription - Before Save - Hide certs in portal | Record-triggered flow (before save) | Hides certification subscriptions from the member portal. | Field default / before-save flow on Membership__c if certification memberships migrate. |  | TBC | UX | Only needed if cert memberships are in Phase 1 data. | No | TBC | TBC
[5 empty] | Total (days) | 5 |  |  |  | No | TBC | TBC
[10 empty] | No | TBC | TBC
[10 empty] | No | TBC | TBC
[10 empty] | No | TBC | TBC
[10 empty] | No | TBC | TBC
[10 empty] | No | TBC | TBC
[10 empty] | No | TBC | TBC
[10 empty] | No | TBC | TBC
[10 empty] | No | TBC | TBC

## 4.5 Portal & Website APIs
4.5 Portal & Website APIs — Phase 1 — Core Membership go-live
# | Automation (API name) | Label (as shown in Setup) | Automation type | What it does today | NPC re-implementation | Estimate (days) | Keep / Ignore (Cirrico rec.) | Layer | Cirrico comments | BSAVA Reviewed | BSAVA - Keep / Ignore | BSAVA - Layer Decision | BSAVA comments
1 | CommunityLoginAPI |  | Apex REST (@RestResource) | WordPress SSO: validates member username/password for portal login (password-proxy pattern). | Replace per D2 with modern SSO (OpenID Connect / Experience Cloud identity) rather than a password proxy. |  | TBC | UX | Blocked by D2. Security uplift opportunity. | No | TBC | TBC
2 | /memberstatus (zen_ws_memberstatus) |  | Apex REST | Returns member status to the website. | Re-expose against Membership__c / Entitlement__c for Timberyard/UXL. |  | TBC | UX | API-contract workstream: agree request/response shapes before build. Shared DTO class ZEN_APIHandler supports these endpoints. | No | TBC | TBC
3 | /checkmemberstatus (ZEN_ws_checkMemberStatus) |  | Apex REST | Checks active status by member name/email + membership number; returns membership type names. | Re-expose against Membership__c. |  | TBC | UX | Contract documented in Legacy Logic & Integration Reference, Section C. | No | TBC | TBC
4 | /getuserdetails (zen_ws_getuserdetails) |  | Apex REST | Returns user/member details to the website. | Re-expose against Person Account / Membership__c. |  | TBC | UX |  | No | TBC | TBC
5 | /mydetails (ZEN_ws_mydetails) |  | Apex REST | Member self-service: personal details. | Re-expose against Person Account. |  | TBC | UX |  | No | TBC | TBC
6 | /myaddresses (ZEN_ws_myAddresses) |  | Apex REST | Member self-service: addresses. | Re-expose against the chosen NPC address model. |  | TBC | UX |  | No | TBC | TBC
7 | /updatepreferences (ZEN_ws_Preferences) |  | Apex REST | Updates member communication preferences. | Re-expose against NPC consent/preference fields (align with D1). |  | TBC | UX |  | No | TBC | TBC
8 | /changepassword (ZEN_ws_ChangePassword) |  | Apex REST | Changes the member's portal password. | Likely superseded by the D2 identity solution. |  | TBC | UX | May be obsolete under OIDC. | No | TBC | TBC
9 | /createcase (ZEN_ws_CreateCase) |  | Apex REST | Creates a support Case from the website. | Re-expose against Case. |  | TBC | UX |  | No | TBC | TBC
10 | /cpdpoints (ZEN_ws_CPDPoints) |  | Apex REST | Returns the member's CPD hours to the website. | Keep the contract; data source moves when CPD migrates (Phase 3). |  | TBC | UX | Confirm whether CPD data is visible at Phase 1 cutover. | No | TBC | TBC
11 | /getebook (ZEN_ws_getebook) |  | Apex REST | Returns eBook access for entitled members. | Re-expose driven by Entitlement__c. |  | TBC | UX | Confirm eBook programme still active. | No | TBC | TBC
12 | /getFormulary (ZEN_ws_getFormulary) |  | Apex REST | Formulary content lookup (Small Animal / Exotics) for entitled members. | Re-expose driven by Entitlement__c + migrated Formulary config. |  | TBC | UX |  | No | TBC | TBC
13 | Portal login redirects (ZEN_Register_Redirect, Zen_LoginFlowController) |  | Aura/Apex controllers | Handle portal login/registration redirects between the website and Salesforce (Site.login + community/WordPress URL settings). | Superseded by the D2 identity design. |  | TBC | UX | SECURITY: ZEN_Register_Redirect contains a hard-coded default password — must not be ported as-is. | No | TBC | TBC
14 | Contact_Screen_Flow_Email_Preferences | Contact - Screen Flow - Email Preferences | Screen flow | Member email-preference management screen (internal/portal). | Rebuild on NPC consent/preference fields. |  | TBC | UX | Align with D1. | No | TBC | TBC
15 | ZEN_JSAP_Controller (Wiley Online Library) |  | Apex callout (@AuraEnabled) | Gets an authenticated journal (JSAP) access URL for entitled members via the Wiley login proxy. | Re-implement driven by Entitlement__c (journal-access badge). |  | TBC | UX | Fast-follow after go-live is acceptable. | No | TBC | TBC
[5 empty] | Total (days) | 0

## 4.6 Contact-User Hygiene
4.6 Contact-User Hygiene — Phase 1 — Core Membership go-live
# | Automation (API name) | Label (as shown in Setup) | Automation type | What it does today | NPC re-implementation | Estimate (days) | Keep / Ignore (Cirrico rec.) | Layer | Cirrico comments | BSAVA Reviewed | BSAVA - Keep / Ignore | BSAVA - Layer Decision | BSAVA comments
1 | Contact_After_Save | Contact - After Save - Sync User | Record-triggered flow | Syncs FirstName/LastName/ContactId from Contact to the community User. | Record-triggered flow in NPC (Person Account model — re-map fields). Only needed if community Users exist (D2). |  | TBC | UX |  | No | TBC | TBC
2 | Update_Primary_Role_On_User_Creation | Update Primary Role on User Creation | Record-triggered flow (before save) | Sets the member's primary role and LMS username on new Users. | Fold into the D2 identity design. |  | TBC | UX |  | No | TBC | TBC
3 | zen_BatchUpdateUserPrimaryRole |  | Batch Apex | Keeps Contact primary role in sync with the User. | Fold into the D2 identity design (reconciliation job). |  | TBC | UX | May be redundant if role travels in the SSO payload. | No | TBC | TBC
4 | Update_mailing_address_on_contact_from_default_KA | KA - After Save - Create/Update - Geographic Region | Record-triggered flow (OrderApi__Known_Address__c) | Copies the default Known Address onto Contact mailing address and derives geographic region (guards invalid state codes). | Depends on the chosen NPC address model. Region derivation via the migrated Region__c / Region_Mapping__c rulebook; migrated stored region values are authoritative. | 2 | Keep | Logic |  | No | TBC | TBC
5 | Email_to_IT_Support_when_Bug_Report_From_App_Created | Email to IT Support when Bug Report From App Created | Record-triggered flow (Case) | Emails IT support when an app bug-report Case is created. | Trivial rebuild (flow + email alert) if Cases move to NPC. |  | Ignore |  |  | No | TBC | TBC
6 | Update_Geo_Region | Update Geo Region | Scheduled flow (ran once) | One-off backfill of Contact geographic region / postcode flags from Known Address. | Handled in the migration ETL — no ongoing automation needed. |  | Ignore |  | Covered by data migration. | No | TBC | TBC
[5 empty] | Total (days) | 2 |  |  |  | No | TBC | TBC
[10 empty] | No | TBC | TBC
[10 empty] | No | TBC | TBC
[10 empty] | No | TBC | TBC
[10 empty] | No | TBC | TBC
[10 empty] | No | TBC | TBC
[10 empty] | No | TBC | TBC
[10 empty] | No | TBC | TBC

## 5. Payments, Finance & DD
5. Payments, Finance & DD — Phase 2 — Payments, Finance & Direct Debit (finance stays in Sage)
# | Automation (API name) | Label (as shown in Setup) | Automation type | What it does today | NPC re-implementation | Estimate (days) | Keep / Ignore (Cirrico rec.) | Layer | Cirrico comments | BSAVA Reviewed | BSAVA - Keep / Ignore | BSAVA - Layer Decision | BSAVA comments
1 | Stripe card payments (Fonteva Registry: payment intents) |  | Packaged payment config | Card payments via Stripe inside Fonteva checkout. | Configure Stripe within the chosen NPC checkout/payment solution (D4). |  |  | UX | Estimate is config + testing; solution selection is D4. | No | TBC | TBC
2 | GoCardless Direct Debit + zen_redirectDDPayment Spark Plug (Zen_redirectDDCookieController) |  | Packaged DD + custom LWC checkout extension + cookie controller | Direct Debit checkout redirect to GoCardless; cookie controller carries order/user context through the redirect; mandate/payment ids synced back. | New DD solution with GoCardless: mandate lifecycle, payment schedules, failure handling. Core Phase 2 build. |  |  | UX | BSAVA is DD-heavy — highest-risk payments item. | No | TBC | TBC
3 | SPL_Scheduled_14_Day_Annual_DD | SPL - Scheduled - 14 Day Annual DD | Scheduled flow (daily 11:00) | Sends the 14-day advance-notice email before annual DD collections — regulatory requirement. | Scheduled flow over the new payment-schedule data. Must ship with the DD solution. | 2 | Keep | Logic | Regulatory — cannot be dropped. | No | TBC | TBC
4 | Receipt_After_Created_Dispatch_Email | Receipt - After Created - Dispatch Email; Dispatch Email | Record-triggered flow | Sends receipt/invoice email when a receipt is created (item-specific logic). | Payment-confirmation comms on the new payment events. |  | TBC | UX | Depends on D1 + D4. | No | TBC | TBC
5 | Zen_Receipt_After_Save_Posted_Receipt | Receipt - After Save - Posted Receipt | Record-triggered flow | Fires the Receipt_Posted email alert when a receipt posts. | Fold into the same payment-confirmation comms design. |  | TBC |  | Unknown - Finance Integration Dependency | No | TBC | TBC
6 | Receipt_Scheduled_Flows_Send_Receipt_DD | Receipt - Scheduled Flows - Send Receipt DD | Scheduled flow (daily) | Sends DD receipt emails on schedule. | Fold into DD payment-confirmation comms. |  | TBC |  | Unknown - Finance Integration Dependency | No | TBC | TBC
7 | Sales_Order_After_Save_Create_Update | Sales Order - After Save - Create/Update | Record-triggered flow | Order housekeeping: duplicate-check fixes, dispatch email alert. | Re-specify on Order — keep dispatch comms; drop Fonteva-specific plumbing. |  | Ignore |  | Review line-by-line during design. | No | TBC | TBC
8 | Sales_Order_Line_After_Save_Update | Sales Order Line - After Save - Create/Update | Record-triggered flow | Updates parent order + item; sets subscription/inventory/shipping/renewal flags. | Re-specify on OrderItem — most flags feed Fonteva plumbing and can be dropped; keep renewal flags. |  | Ignore |  | Review line-by-line during design. | No | TBC | TBC
9 | NPC -> Sage Intacct integration (replaces zen_SageFinanceExport pipeline) |  | Scheduled batch + XML API client (zen_SchedulePostTransactions, zen_SageFinanceExport, Zen_IntAcct_APICall, Zen_XMLParser, ZEN_Batch_UpdateFinanceExport + invocables zen_flowaction_SageExport, Zen_flowaction_PostTransactions) | Daily: flags duplicate transactions then posts Fonteva Transactions (invoices/receipts/disbursements/credit notes) to Sage Intacct; logs export batches, writes back Sage keys. | NOT a port — new design (D5). Fonteva Transactions won't exist; define what NPC sends to Sage (order/payment summaries vs payment-provider feeds) and build accordingly. |  | TBC |  | Estimate placeholder until D5 design is agreed. | No | TBC | TBC
10 | zen_flowActionPostSalesOrder |  | Invocable Apex | Posts/closes a Sales Order from flows (sets Status=Closed, Is_Closed=true); used by the donation bridge and order flows. | NPC Order activation is standard platform behaviour — likely retire; confirm no residual need in the new order flows. |  | TBC |  |  | No | TBC | TBC
11 | Post_Transaction_Lines_to_SageIntAcct / Push_Data_to_Sage_by_Date | Post Transaction Lines to SageIntAcct; Push Data to Sage by Date | Screen flows | Manual staff triggers to push transactions/date ranges to Sage. | Superseded by the new integration's manual-run capability. | 0 | TBC |  | Cover manual re-run in the new integration design. | No | TBC | TBC
12 | Transaction_On_Update_Transaction_Fix | Transaction - On Update - Transaction Fix | Record-triggered flow | Re-posts transactions via Apex on update. | Retire with Fonteva finance. | 0 | TBC |  |  | No | TBC | TBC
13 | Transaction_Line_Scheduled | Transaction Line - Scheduled | Scheduled flow (daily) | Nightly tax/type reconciliation onto Fonteva Transactions. | Retire — reconciliation moves to Sage / the new integration. | 0 | TBC |  |  | No | TBC | TBC
14 | Order financial rollups (SO_VAT_Total, SO_Tax_Code_00/01/99, SO_Shipping, SO_Total_Discount, SO_Sales_Order_Lines + scheduled variants; triggers dlrs_OrderApi_Sales_Order_LineTrigger + Zen_SOL_CalculateRollups; async recalc flow Zen_Calculate_SO_DLRS_Rollups_Asyncronously) | Calculate SO DLRS Rollups Asyncronously | DLRS rollups + triggers + record-triggered flow | Aggregate line-level VAT / tax-code / shipping / discount totals and line counts onto the Sales Order for invoices, receipts and Sage export. | Rebuild only what the NPC invoice/Sage design needs, as OrderItem->Order record-triggered flow aggregations. |  | TBC |  | Scope depends on D5 — NPC may not need the VAT breakdown on Order. | No | TBC | TBC
15 | ItemToReceipt rollup |  | DLRS rollup | Concatenates receipt line descriptions onto the Receipt (used in receipt emails). | Fold into receipt comms design if needed. |  | TBC |  |  | No | TBC | TBC
16 | SOCountReceipts / SOCountCashTransactions rollups |  | DLRS rollups | Counts receipts and cash transactions per Sales Order. | Retire with Fonteva finance objects. |  | TBC |  |  | No | TBC | TBC
17 | Opportunity_After_Save_Create_Donation_in_Fonteva | Opportunity - After Save - Create Donation in Fonteva | Record-triggered flow (Opportunity) | Builds a full Fonteva sales order + EPayment for donation Opportunities. | Retire — NPC native fundraising/giving replaces the bridge. Confirm donation payment path in D4. |  | TBC |  | Confirm donations approach with BSAVA. | No | TBC | TBC
18 | ZEN_CheckoutRedirect (Gift Aid) |  | Apex/LWC | Captures the Gift Aid declaration during checkout redirect. | Rebuild Gift Aid capture in the new checkout; store declarations on NPC's Gift Aid model. |  | Keep | UX |  | No | TBC | TBC
19 | Dedup utilities (Find_Duplicates_Sales_Orders_and_Removed, zen_Batch_DeleteRecords, zen_Batch_DeleteSchPaymentRecords + invocables zen_FlowAction_FindDuplicates, zen_FlowAction_Delete, zen_FlowAction_FindSchDuplicates, zen_FlowAction_SchPaymentDelete) | Find Duplicates Sales Orders and Removed | Screen flows + batch Apex + invocables | Find-and-delete tooling for duplicate subscription order lines and scheduled payments. | Do not port — compensates for Fonteva-specific duplication bugs. |  | Ignore |  | Revisit only if the new renewal engine misbehaves. | No | TBC | TBC
20 | ZEN_FinanceExport (CSV export UI) |  | LWC + Apex controller | Staff finance CSV export screen. | Fold into the D5 finance design. |  | TBC |  |  | No | TBC | TBC
21 | Redirect_to_Zen_Invoice_Template_Screenflow | Redirect to Zen Invoice Template Screenflow | Screen flow (redirect) | Redirects to the Zen invoice template. | Invoice documents generated from the new order model. |  | TBC |  |  | No | TBC | TBC
[5 empty] | Total (days) | 2

## 6. Events, CPD & LMS
6. Events, CPD & LMS — Phase 3 — Events, CPD & Learning (needs a replacement events solution first; estimates indicative)
# | Automation (API name) | Label (as shown in Setup) | Automation type | What it does today | NPC re-implementation | Estimate (days) | Keep / Ignore (Cirrico rec.) | Layer | Cirrico comments | BSAVA Reviewed | BSAVA - Keep / Ignore | BSAVA - Layer Decision | BSAVA comments
1 | Attendee_After_Save_Create_Update | Attendee - After Save - Create / Update | Record-triggered flow | Event confirmation emails by event type (Congress, Hybrid, In-Person, Lumos, Online, Regional). | Rebuild on the replacement events solution's attendee object. |  | TBC |  | Estimates assume a Salesforce-based events solution. | No | TBC | TBC
2 | Attendee_Scheduled_Event_Reminder | Attendee - Scheduled - Event Reminder | Scheduled flow (daily) | Pre-event reminder emails by format; creates EmailMessage records. | Reminder cadence on the new solution. |  | TBC |  |  | No | TBC | TBC
3 | Attendee_Scheduled_Regional_Reminder | Attendee - Scheduled - Regional Reminder | Scheduled flow (daily) | Regional-event reminder emails. | Reminder cadence on the new solution. |  | TBC |  |  | No | TBC | TBC
4 | Attendee_Scheduled_Lumos_Lapse | Attendee - Scheduled - Lumos Lapse | Scheduled flow (daily) | Marks Lumos attendees lapsed. | Status automation on the new solution. |  | TBC |  | Confirm Lumos programme continues. | No | TBC | TBC
5 | Attendee_Autolaunched_Certificate_Link | Attendee - Autolaunched - Certificate Link | Button/launched flow | Sends post-event certificate-link email. | Rebuild as event-comms action. |  | TBC |  |  | No | TBC | TBC
6 | Attendee_Autolaunched_Recording_Link | Attendee - Autolaunched - Recording Link | Button/launched flow | Sends post-event recording-link email. | Rebuild as event-comms action. |  | TBC |  |  | No | TBC | TBC
7 | Attendee_Autolaunched_Event_Cancellation | Attendee - Autolaunched - Event Cancellation | Button/launched flow | Sends cancellation/postponement emails (in-person/online/webinar variants). | Rebuild as event-comms action. |  | TBC |  |  | No | TBC | TBC
8 | Send_Email_for_Attendee_List + batchFlowSendEmail | Send Email for Attendee List | Screen flow + batch Apex | Bulk email to a selected attendee list (template + CC/BCC/attachments). | Bulk-comms tooling on the new solution (or the D1 email platform's native send). |  | TBC |  |  | No | TBC | TBC
9 | Close_Old_Events_Automated | Close Old Events; Close Old Events Automated | Scheduled flow (daily) | Closes and unpublishes past events. | Housekeeping automation on the new solution. |  | TBC |  |  | No | TBC | TBC
10 | Zen_Venue_After_Save_Update_Venue_Field_on_Event | Venue - After Save - Update Venue Field on Event | Record-triggered flow | Sets the primary venue field on the related event. | Likely native in the new solution. |  | TBC |  |  | No | TBC | TBC
11 | Speaker_Engagement_Before_Save_Record_Update | Speaker Engagement - Before Save - Record Update | Record-triggered flow (before save) | Copies biography text from the speaker-biography record onto the engagement. | Rebuild if the speaker model carries over. |  | TBC |  |  | No | TBC | TBC
12 | Event rollups (Zen_Event_Speakers, Event_Community_Site) |  | DLRS rollups | Speaker-name concatenation (display order) and community-site count on the event. | Rollup flows on the new solution if needed. |  | TBC |  |  | No | TBC | TBC
13 | Zen_Event_Request_Form | Event Request Form | Screen flow | Regional event request form. | Rebuild on the new solution. |  | TBC |  |  | No | TBC | TBC
14 | Zen_Regional_Events_View_Attendees | Regional Events Screen Flow | Screen flow | Staff view of regional-event attendees. | Rebuild (may be a list view/report instead). |  | TBC |  |  | No | TBC | TBC
15 | Certification_Events | Certification Events | Screen flow | Attendee-facing view of registered events. | Rebuild on the new solution/portal. |  | TBC |  |  | No | TBC | TBC
16 | Moodle enrolment (zen_MoodleEnrolCourse) |  | Invocable Apex (REST callout) | Enrols a user in a Moodle course on purchase. | Re-point enrolment to the new order model; align with LMS SSO username design (D2). |  | TBC |  |  | No | TBC | TBC
17 | Moodle completion sync (zen_ScheduleMoodleCourses -> zen_MoodleCourses; helpers zen_MoodleCourseCompletionStatus, zen_MoodleUserDetails) |  | Scheduled batch Apex (REST callout) + JSON parsers | Nightly sync of Moodle course completions into CPD Hours records. NOTE: endpoint hard-coded to a UAT URL in the snapshot. | Keep the completion -> CPD sync pattern; externalise the endpoint (named credential). |  | TBC |  | Verify the production endpoint (D6). | No | TBC | TBC
18 | CPD_Hours_Screen_Flow_Portal_View | CPD Hours - Screen Flow - Portal View | Screen flow | Member-portal view of CPD hours. | Rebuild when CPD data migrates. |  | TBC |  |  | No | TBC | TBC
19 | General_Meeting_Email_Reminder | General Meeting - Email Reminder | Scheduled flow (ran once) | One-off AGM reminder to eligible member types. | One-off — recreate ad hoc if needed. |  | TBC |  |  | No | TBC | TBC
[5 empty] | Total (days) | 0

## 7. Committees, Vols & Certs
7. Committees, Vols & Certs — Phase 4 — Committees, Volunteers & Certifications
# | Automation (API name) | Label (as shown in Setup) | Automation type | What it does today | NPC re-implementation | Estimate (days) | Keep / Ignore (Cirrico rec.) | Layer | Cirrico comments | BSAVA Reviewed | BSAVA - Keep / Ignore | BSAVA - Layer Decision | BSAVA comments
1 | Volunteer_Create_Update | Volunteer - Create/Update | Record-triggered flow | Creates a volunteer Badge and updates the Contact for new volunteers. | Rebuild when volunteers move; volunteer badge becomes an Entitlement__c. | 1.5 | Keep | Logic |  | No | TBC | TBC
2 | Zen_Volunteer_Application_Form | Volunteer Application Form | Screen flow | Volunteer application form. | Rebuild on the volunteers model. |  | Keep | UX |  | No | TBC | TBC
3 | Tenure_Before_Save | Tenure - Before Save | Record-triggered flow (before save) | Defaults tenure start/end dates. | Before-save flow on the new tenure object. |  | Ignore |  |  | No | TBC | TBC
4 | Tenure_After_Save | Tenure - After Save | Record-triggered flow | Updates committee-membership role fields from the tenure. | Record-triggered flow on tenure. |  | Ignore |  |  | No | TBC | TBC
5 | End_date_less_than_start_date (Zen_Tenure__c) |  | Validation rule | Tenure end date cannot precede start date. | Recreate on the new tenure object. | 0.25 | Keep | Logic |  | No | TBC | TBC
6 | Committee rollups (Zen_Active_Role, Zen_Committee_Memberships) |  | DLRS rollups + trigger | Concatenates active roles and committee names onto the Volunteer. | Rollup flows on the committees model. | 1 | Keep | Logic |  | No | TBC | TBC
7 | Screen_Flow_Application_PG_Cert | Screen Flow - Application - Certification | Screen flow | Postgraduate Certificate application (deposit check). | Rebuild against the certifications model + Order for deposits. |  | TBC | UX |  | No | TBC | TBC
8 | Screen_Flow_Application_Approve_PG_Cert | Screen Flow - Application - Approve PG Cert | Screen flow | Staff approval of PG Cert applications. | Rebuild. | 1 | Keep | Logic |  | No | TBC | TBC
9 | Screen_Flow_Application_Generate_Proforma | Screen Flow - Application - Generate Proforma | Screen flow | Generates a proforma invoice from the application. | Rebuild on Order. |  | TBC |  |  | No | TBC | TBC
10 | PG_Cert_Create_Deposit_Send_Form | Screen Flow - PG Cert - Create Deposit & Send Form | Screen flow | Creates the PG Cert deposit sales order and sends the form. | Rebuild on Order. |  | TBC |  |  | No | TBC | TBC
11 | Screen_Flow_PG_Cert_Remaining_Balance_SO_Form | Screen Flow - PG Cert - Remaining Balance SO & Form | Screen flow | Creates the remaining-balance sales order for PG Cert. | Rebuild on Order. |  | TBC |  |  | No | TBC | TBC
12 | Sales_Order_Autolaunched_Send_PG_Renewal | Sales Order - Autolaunched - Send PG Renewal | Launched flow | Sends the PG Cert deposit/renewal email alert. | Rebuild with the D1 email platform. | 1 | Keep | Logic |  | No | TBC | TBC
13 | Scheduled_Certification_Candidate_Update_Current_Subscription | Scheduled - Certification Candidate - Update Current Subscription | Scheduled flow (daily) | Keeps each certification candidate's current-subscription link and status up to date. | Scheduled flow re-pointed to Membership__c. |  | TBC |  |  | No | TBC | TBC
14 | Send_Lapse_Email_Button | Send Lapse Email Button | Button flow | Staff button to send a lapse email. | Quick action on Membership__c. | 0.5 | Keep | Logic | Could pull forward to Phase 1 comms. | No | TBC | TBC
[5 empty] | Total (days) | 5.25

## 8. Not Migrating
8. Not Migrating — Recommended exclusions — please confirm each
# | Automation (API name) | Label (as shown in Setup) | Automation type | What it does today | NPC re-implementation | Estimate (days) | Keep / Ignore (Cirrico rec.) | Layer | Cirrico comments | BSAVA comments
1 | FPS__Assign_Community_Users, FPS__Assign_Guest_Users, FPS__Assign_Staff_Users, FPS__Assign_Users_to_Group | Fonteva: Assign Community Users; Fonteva: Assign Guest Users; Fonteva: Assign Staff Users; Fonteva: Assign Users to Permission Set Group | Managed-package flows (4) | Fonteva permission-set assignment for community/guest/staff users. | Not applicable — NPC permission-set design replaces the FPS package. | 0 | Ignore
2 | FPS__Check_Permission_Set_Group, FPS__Check_Security, FPS__Check_Sharing_Sets, FPS__Check_Sharing_Settings, FPS__Clear_Profiles, FPS__Run_Flow | Fonteva: Run Flow; Fonteva: Clear Profiles; Fonteva: Check Security; Fonteva: Check Sharing Sets; Fonteva: Check Sharing Settings; Fonteva: Check Permission Set Group | Managed-package flows (6) | Fonteva security/sharing checks and profile utilities. | Not applicable. | 0 | Ignore
3 | DEBUG_Send_Email_Test | DEBUG - Send Email Test | Screen flow (Draft) | Debug email test flow. | Test utility. | 0 | Ignore
4 | Send_Better_Email_Testflow + sendBetterEmail_Test_Create_Test_Templates_if_needed | Send Better Email Testflow; sendBetterEmail Test - Create Test Templates if Needed | Flows (Draft) | SendBetterEmail package test flows. | Test utility; package not carried forward. | 0 | Ignore
5 | Datatable_Configuration_Wizard | Datatable Configuration Wizard | Screen flow (Draft) | Config wizard for the datatable LWC component package. | Utility package tooling. | 0 | Ignore
6 | Dispatch_Email | Dispatch Email | Autolaunched flow (Obsolete) | Waited 30 min then fired the dispatch email alert. | Superseded by Receipt_After_Created_Dispatch_Email. | 0 | Ignore
7 | Receipt_After_Save_Posted_Receipt | Receipt - After Save - Posted Receipt | Record-triggered flow (Obsolete) | Fired the Receipt_Posted alert. | Superseded by Zen_Receipt_After_Save_Posted_Receipt. | 0 | Ignore
8 | Send_BSAVA_App_Trial_Expiration_Notice | Send BSAVA App Trial Expiration Notice; App Trial | Record-triggered flow (Obsolete) | Trial-expiry email. | Superseded by App_Trial_Lapse_Emails cadence. | 0 | Ignore
9 | Zen_Update_Primary_Role_in_User_After_Contact_Updated | Update Primary Role in User After Contact Updated | Record-triggered flow (Obsolete) | User role sync after contact update. | Superseded by active role-sync automations. | 0 | Ignore
10 | Sub_Flow_Known_Address_Sync | Sub Flow - Known Address Sync | Screen subflow (Obsolete) | Known-address sync screen. | Obsolete. | 0 | Ignore
11 | Subscription_Override_Fix | Subscription Override Fix | Scheduled flow (Obsolete) | Data fix toggling renewal override. | One-off data fix. | 0 | Ignore
12 | Term_Scheduled_Auto_Renewal_Smart_Emails | Term - Scheduled - Auto Renewal Smart Emails | Scheduled flow (Obsolete) | Original multi-stage renewal email cadence ('Temp - disabled once used'). | The cadence itself is re-created in tab 4.2 (Send_Renewal_Reminder_Email row). | 0 | Ignore |  | Reference for cadence design.
13 | Screen_Flow_Sales_Order_Cert_Renewal_Email | Screen Flow - Sales Order - Cert Renewal Email | Screen flow (Obsolete) | Cert renewal email form. | Obsolete. | 0 | Ignore
14 | New_Overall_Total / Sales_Order_Line_Scheduled | Sales Order Line - Scheduled; New Overall Total | Scheduled flows (Obsolete) | One-off order-total and tax-code data fixes. | One-off data fixes. | 0 | Ignore
15 | Calculate_SO_DLRS_Rollups_Asyncronously_on_Delete | Calculate SO DLRS Rollups Asyncronously on Delete | Record-triggered flow (Draft) | DLRS recalc on delete (never activated). | Covered by the rollup rebuild in tab 5. | 0 | Ignore
16 | Close_Old_Events | Close Old Events | Flow (Draft) | Predecessor of Close_Old_Events_Automated. | Superseded. | 0 | Ignore
17 | Find_Duplicates_SchedulePayments_and_Removed / Screen_Flow_Transactions_Fix / Import_PDF_Config | Import PDF Config; Find Duplicates SchedulePayments and Removed; Screen Flow - Transactions Fix | Flows (Draft) | Draft admin/data-fix utilities. | Never activated. | 0 | Ignore
18 | Update_username_for_LMS_SSO | Update username for LMS SSO | Record-triggered flow (Draft) | Would set Username/LMS username for LMS SSO. | Intent folded into the D2 identity design. | 0 | Ignore
19 | FixSOTransactionsBatch |  | Batch Apex | One-off invoice->receipt posting rebuild with hard-coded GL ids. | Historic remediation. | 0 | Ignore
20 | Item_has_catalog / Item_to_sales_order / Legacy_Invoices_Goods_VAT20 rollups |  | DLRS rollups | Fonteva catalog counts, item concat (inactive) and legacy-invoice VAT sum. | Fonteva catalog / legacy objects not migrating. | 0 | Ignore
21 | SendBetterEmail package (SendBetterEmail, SendBetterEmailAddAttachmentToEmail, SendBetterEmailAddTasksToEmail, SendBetterEmailBulk, SendBetterEmailBulkRequestSetup, SendBetterEmailConstant, SendBetterEmailRequest, SendBetterEmailResponse, SendBetterEmailUtil, FlowEmailComposerCtrl) |  | Open-source Apex package | The email-send engine behind ~30 flows. | Replaced wholesale by the D1 email platform decision — do not port the classes. | 0 | Ignore |  | While the flow package can be ignored. I want to know if there are any emails/comms that are in use for us to migrate to SF/Marketing Cloud
22 | Datatable/UI utility packages (ers_DatatableController, ers_EncodeDecodeURL, ers_QueryNRecords, pdfConfigController, pdfGeneratorController, viewzController, zenDataTableController, QuickLightningLookupController, FieldPickerController, picklist_Controller) |  | Open-source / utility Apex+LWC | Screen-flow datatable, PDF generation, lookup and picklist UI utilities. | Reinstall current open-source equivalents in NPC if the rebuilt screen flows need them. | 0 | Ignore
23 | Custom portal UI controllers (zenMemberLinkController, zenRecordFormController, zenFormField, ZEN_APIHandler) |  | Apex controllers / DTOs | Custom UI helpers for the member portal (record forms, member links, field-set DTOs, API data shapes). | Portal UI is rebuilt in the D2 design — carry the requirements, not the code. | 0 | Ignore
24 | Internal utility classes (AnalyticsUtils, ConfigsPickList, EncryptionUtil, ExportReportToJSONController, TabularReportResponse, FieldData, FieldDef, sObjectUtils, Zen_GuidUtil) |  | Apex utilities | Report export, encryption, field-describe and misc helpers used by the above. | Port only if a kept automation needs them; none is an automation itself. | 0 | Ignore
25 | Standard community scaffolding (ChangePasswordController, CommunitiesLandingController, CommunitiesLoginController, CommunitiesSelfRegConfirmController, CommunitiesSelfRegController, ForgotPasswordController, LightningForgotPasswordController, LightningLoginFormController, LightningSelfRegisterController, MicrobatchSelfRegController, MyProfilePageController, SiteLoginController, SiteRegisterController) |  | Salesforce-generated controllers | Default Experience Cloud login/registration scaffolding. | Regenerated automatically when the NPC community is created. | 0 | Ignore
26 | Fonteva Framework__Registry (39 records) + Spark Plug registry |  | Managed-package config | Stripe/captcha/runOnce/renewal-batch configuration. | Documents behaviour to replace (D3/D4); not portable. | 0 | Ignore
[5 empty] | Total (days) | 0

## 9. Flow Register
9. Flow Register — auto-generated from the metadata snapshot; every item maps to a sign-off row
Flow API name | Label (as shown in Setup) | Kind | Status | Covered in tab
App_Trial | App Trial | Screen/launched | Active | 4.1 Joining & Applications
App_Trial_Lapse_Emails | App Trial - Lapse Emails | Scheduled | Active | 4.1 Joining & Applications
Application_After_Save_Update | Application - After Save - Update | Record-triggered (after) | Active | 4.1 Joining & Applications
Attendee_After_Save_Create_Update | Attendee - After Save - Create / Update | Record-triggered (after) | Active | 6. Events, CPD & LMS
Attendee_Autolaunched_Certificate_Link | Attendee - Autolaunched - Certificate Link | Screen/launched | Active | 6. Events, CPD & LMS
Attendee_Autolaunched_Event_Cancellation | Attendee - Autolaunched - Event Cancellation | Screen/launched | Active | 6. Events, CPD & LMS
Attendee_Autolaunched_Recording_Link | Attendee - Autolaunched - Recording Link | Screen/launched | Active | 6. Events, CPD & LMS
Attendee_Scheduled_Event_Reminder | Attendee - Scheduled - Event Reminder | Scheduled | Active | 6. Events, CPD & LMS
Attendee_Scheduled_Lumos_Lapse | Attendee - Scheduled - Lumos Lapse | Scheduled | Active | 6. Events, CPD & LMS
Attendee_Scheduled_Regional_Reminder | Attendee - Scheduled - Regional Reminder | Scheduled | Active | 6. Events, CPD & LMS
Badge_Before_Save_Create | Badge - Before Save - Create | Record-triggered (before) | Active | 4.4 Entitlements & SSO
CPD_Hours_Screen_Flow_Portal_View | CPD Hours - Screen Flow - Portal View | Screen/launched | Active | 6. Events, CPD & LMS
CVFindSubscriptionSubFlow | CVFindSubscriptionSubFlow | Autolaunched | Active | 4.1 Joining & Applications
CVSApplicationSubflow | CVSUpdateContactSubflow | Screen/launched | Active | 4.1 Joining & Applications
CV_Sales_Order_Subflow | CV Sales Order Subflow | Autolaunched | Active | 4.1 Joining & Applications
Calculate_SO_DLRS_Rollups_Asyncronously_on_Delete | Calculate SO DLRS Rollups Asyncronously on Delete | Record-triggered (after) | Draft | 8. Not Migrating
Cancel_Expired_Proformas | Cancel Expired Proformas | Scheduled | Active | 4.2 Renewals
Certification_Events | Certification Events | Screen/launched | Active | 6. Events, CPD & LMS
Close_Old_Events | Close Old Events | Screen/launched | Draft | 6. Events, CPD & LMS
Close_Old_Events_Automated | Close Old Events Automated | Scheduled | Active | 6. Events, CPD & LMS
Contact_After_Save | Contact - After Save - Sync User | Record-triggered (after) | Active | 4.6 Contact-User Hygiene
Contact_Screen_Flow_Email_Preferences | Contact - Screen Flow - Email Preferences | Screen/launched | Active | 4.5 Portal & Website APIs
DEBUG_Send_Email_Test | DEBUG - Send Email Test | Screen/launched | Draft | 8. Not Migrating
Datatable_Configuration_Wizard | Datatable Configuration Wizard | Screen/launched | Draft | 8. Not Migrating
Dispatch_Email | Dispatch Email | Autolaunched | Obsolete | 5. Payments, Finance & DD
Email_to_IT_Support_when_Bug_Report_From_App_Created | Email to IT Support when Bug Report From App Created | Record-triggered (after) | Active | 4.6 Contact-User Hygiene
FPS__Assign_Community_Users | Fonteva: Assign Community Users | Screen/launched | ? | 8. Not Migrating
FPS__Assign_Guest_Users | Fonteva: Assign Guest Users | Screen/launched | ? | 8. Not Migrating
FPS__Assign_Staff_Users | Fonteva: Assign Staff Users | Screen/launched | ? | 8. Not Migrating
FPS__Assign_Users_to_Group | Fonteva: Assign Users to Permission Set Group | Screen/launched | ? | 8. Not Migrating
FPS__Check_Permission_Set_Group | Fonteva: Check Permission Set Group | Screen/launched | ? | 8. Not Migrating
FPS__Check_Security | Fonteva: Check Security | Screen/launched | ? | 8. Not Migrating
FPS__Check_Sharing_Sets | Fonteva: Check Sharing Sets | Screen/launched | ? | 8. Not Migrating
FPS__Check_Sharing_Settings | Fonteva: Check Sharing Settings | Screen/launched | ? | 8. Not Migrating
FPS__Clear_Profiles | Fonteva: Clear Profiles | Screen/launched | ? | 8. Not Migrating
FPS__Run_Flow | Fonteva: Run Flow | Screen/launched | ? | 8. Not Migrating
Find_Duplicates_Sales_Orders_and_Removed | Find Duplicates Sales Orders and Removed | Screen/launched | Active | 5. Payments, Finance & DD
Find_Duplicates_SchedulePayments_and_Removed | Find Duplicates SchedulePayments and Removed | Screen/launched | Draft | 8. Not Migrating
General_Meeting_Email_Reminder | General Meeting - Email Reminder | Scheduled | Active | 6. Events, CPD & LMS
Import_PDF_Config | Import PDF Config | Screen/launched | Draft | 8. Not Migrating
Member_Benefit_After_Save_Create_Update | Member Benefit - After Save - Create/Update | Record-triggered (after) | Active | 4.3 Benefits
New_Overall_Total | New Overall Total | Scheduled | Obsolete | 8. Not Migrating
Opportunity_After_Save_Create_Donation_in_Fonteva | Opportunity - After Save - Create Donation in Fonteva | Record-triggered (after) | Active | 5. Payments, Finance & DD
PG_Cert_Create_Deposit_Send_Form | Screen Flow - PG Cert - Create Deposit & Send Form | Screen/launched | Active | 7. Committees, Vols & Certs
Post_Transaction_Lines_to_SageIntAcct | Post Transaction Lines to SageIntAcct | Screen/launched | Active | 5. Payments, Finance & DD
Push_Data_to_Sage_by_Date | Push Data to Sage by Date | Screen/launched | Active | 5. Payments, Finance & DD
Receipt_After_Created_Dispatch_Email | Receipt - After Created - Dispatch Email | Record-triggered (after) | Active | 5. Payments, Finance & DD
Receipt_After_Save_Posted_Receipt | Receipt - After Save - Posted Receipt | Record-triggered (after) | Obsolete | 5. Payments, Finance & DD
Receipt_Scheduled_Flows_Send_Receipt_DD | Receipt - Scheduled Flows - Send Receipt DD | Scheduled | Active | 5. Payments, Finance & DD
Redirect_to_Zen_Invoice_Template_Screenflow | Redirect to Zen Invoice Template Screenflow | Screen/launched | Active | 5. Payments, Finance & DD
SPL_Scheduled_14_Day_Annual_DD | SPL - Scheduled - 14 Day Annual DD | Scheduled | Active | 5. Payments, Finance & DD
Sales_Order_After_Save_Create_Update | Sales Order - After Save - Create/Update | Record-triggered (after) | Active | 5. Payments, Finance & DD
Sales_Order_Autolaunched_Send_PG_Renewal | Sales Order - Autolaunched - Send PG Renewal | Screen/launched | Active | 7. Committees, Vols & Certs
Sales_Order_Autolaunched_Welcome_Email1 | Sales Order - Autolaunched - Welcome Email | Screen/launched | Active | 4.1 Joining & Applications
Sales_Order_Line_After_Save_Update | Sales Order Line - After Save - Create/Update | Record-triggered (after) | Active | 5. Payments, Finance & DD
Sales_Order_Line_Scheduled | Sales Order Line - Scheduled | Scheduled | Obsolete | 8. Not Migrating
Sales_Order_Scheduled_Void_Old_Orders | Sales Order - Scheduled - Void Old Orders | Scheduled | Active | 4.2 Renewals
Scheduled_Certification_Candidate_Update_Current_Subscription | Scheduled - Certification Candidate - Update Current Subscription | Scheduled | Active | 7. Committees, Vols & Certs
Screen_Flow_Application_Approve_PG_Cert | Screen Flow - Application - Approve PG Cert | Screen/launched | Active | 7. Committees, Vols & Certs
Screen_Flow_Application_Generate_Proforma | Screen Flow - Application - Generate Proforma | Screen/launched | Active | 7. Committees, Vols & Certs
Screen_Flow_Application_PG_Cert | Screen Flow - Application - Certification | Screen/launched | Active | 7. Committees, Vols & Certs
Screen_Flow_CV_Join_Process | Screen Flow - CV Join Process | Screen/launched | Active | 4.1 Joining & Applications
Screen_Flow_Join_Process | Screen Flow - Join Process | Screen/launched | Active | 4.1 Joining & Applications
Screen_Flow_PG_Cert_Remaining_Balance_SO_Form | Screen Flow - PG Cert - Remaining Balance SO & Form | Screen/launched | Active | 7. Committees, Vols & Certs
Screen_Flow_Sales_Order_Cert_Renewal_Email | Screen Flow - Sales Order - Cert Renewal Email | Screen/launched | Obsolete | 8. Not Migrating
Screen_Flow_Sales_Order_Renewal_Form | Screen Flow - Sales Order - Renewal Form | Screen/launched | Active | 4.2 Renewals
Screen_Flow_Transactions_Fix | Screen Flow - Transactions Fix | Screen/launched | Draft | 8. Not Migrating
Send_BSAVA_App_Trial_Expiration_Notice | Send BSAVA App Trial Expiration Notice | Record-triggered (after) | Obsolete | 8. Not Migrating
Send_Better_Email_Testflow | Send Better Email Testflow | Screen/launched | Draft | 8. Not Migrating
Send_Email_for_Attendee_List | Send Email for Attendee List | Screen/launched | Active | 6. Events, CPD & LMS
Send_Lapse_Email_Button | Send Lapse Email Button | Screen/launched | Active | 7. Committees, Vols & Certs
Send_Renewal_Reminder_Email | Send Renewal Reminder Email | Record-triggered (after) | Active | 4.2 Renewals
Speaker_Engagement_Before_Save_Record_Update | Speaker Engagement - Before Save - Record Update | Record-triggered (before) | Active | 6. Events, CPD & LMS
Sub_Flow_Known_Address_Sync | Sub Flow - Known Address Sync | Screen/launched | Obsolete | 8. Not Migrating
Sub_Flow_Member_Application_Form | Sub Flow - Member Application Form | Screen/launched | Active | 4.1 Joining & Applications
Sub_Flow_Membership_Types_to_display | Sub Flow - Membership Types to display | Autolaunched | Active | 4.1 Joining & Applications
Sub_Flow_Subscription_Plans_to_display | Sub Flow - Subscription Plans to display | Autolaunched | Active | 4.1 Joining & Applications
Subscription_Before_Save_Hide_certs_in_portal | Subscription - Before Save - Hide certs in portal | Record-triggered (before) | Active | 4.4 Entitlements & SSO
Subscription_Override_Fix | Subscription Override Fix | Scheduled | Obsolete | 8. Not Migrating
Tenure_After_Save | Tenure - After Save | Record-triggered (after) | Active | 7. Committees, Vols & Certs
Tenure_Before_Save | Tenure - Before Save | Record-triggered (before) | Active | 7. Committees, Vols & Certs
Term_Scheduled_Auto_Renewal_Smart_Emails | Term - Scheduled - Auto Renewal Smart Emails | Scheduled | Obsolete | 8. Not Migrating
Term_Scheduled_Loyalty_Gift_Benefits | Term - Scheduled - Loyalty Gift / Benefits | Scheduled | Active | 4.3 Benefits
Transaction_Line_Scheduled | Transaction Line - Scheduled | Scheduled | Active | 5. Payments, Finance & DD
Transaction_On_Update_Transaction_Fix | Transaction - On Update - Transaction Fix | Record-triggered (after) | Active | 5. Payments, Finance & DD
Update_Geo_Region | Update Geo Region | Scheduled | Active | 4.6 Contact-User Hygiene
Update_Primary_Role_On_User_Creation | Update Primary Role on User Creation | Record-triggered (before) | Active | 4.6 Contact-User Hygiene
Update_User_Badge | Update User Badge | Record-triggered (after) | Active | 4.4 Entitlements & SSO
Update_mailing_address_on_contact_from_default_KA | KA - After Save - Create/Update - Geographic Region | Record-triggered (after) | Active | 4.6 Contact-User Hygiene
Update_username_for_LMS_SSO | Update username for LMS SSO | Record-triggered (before) | Draft | 8. Not Migrating
Volunteer_Create_Update | Volunteer - Create/Update | Record-triggered (after) | Active | 7. Committees, Vols & Certs
Zen_Calculate_SO_DLRS_Rollups_Asyncronously | Calculate SO DLRS Rollups Asyncronously | Record-triggered (after) | Active | 5. Payments, Finance & DD
Zen_Event_Request_Form | Event Request Form | Screen/launched | Active | 6. Events, CPD & LMS
Zen_Receipt_After_Save_Posted_Receipt | Receipt - After Save - Posted Receipt | Record-triggered (after) | Active | 5. Payments, Finance & DD
Zen_Regional_Events_View_Attendees | Regional Events Screen Flow | Screen/launched | Active | 6. Events, CPD & LMS
Zen_Update_Primary_Role_in_User_After_Contact_Updated | Update Primary Role in User After Contact Updated | Record-triggered (after) | Obsolete | 8. Not Migrating
Zen_Venue_After_Save_Update_Venue_Field_on_Event | Venue - After Save - Update Venue Field on Event | Record-triggered (after) | Active | 6. Events, CPD & LMS
Zen_Volunteer_Application_Form | Volunteer Application Form | Screen/launched | Active | 7. Committees, Vols & Certs
selfRegister | selfRegister | Screen/launched | Active | 4.1 Joining & Applications
sendBetterEmail_Test_Create_Test_Templates_if_needed | sendBetterEmail Test - Create Test Templates if Needed | Screen/launched | Draft | 8. Not Migrating

## 10. Apex Register
10. Apex Register — auto-generated from the metadata snapshot; every item maps to a sign-off row
Apex class | Kind | Covered in tab / disposition
AnalyticsUtils | Class | 8. Not Migrating
AnalyticsUtilsTest | Test / mock | — (test code, no migration action)
ChangePasswordController | Class | 8. Not Migrating
ChangePasswordControllerTest | Test / mock | — (test code, no migration action)
CommunitiesLandingController | Class | 8. Not Migrating
CommunitiesLandingControllerTest | Test / mock | — (test code, no migration action)
CommunitiesLoginController | Class | 8. Not Migrating
CommunitiesLoginControllerTest | Test / mock | — (test code, no migration action)
CommunitiesSelfRegConfirmController | Class | 8. Not Migrating
CommunitiesSelfRegConfirmControllerTest | Test / mock | — (test code, no migration action)
CommunitiesSelfRegController | Class | 8. Not Migrating
CommunitiesSelfRegControllerTest | Test / mock | — (test code, no migration action)
CommunityLoginAPI | REST API | 4.5 Portal & Website APIs
CommunityLoginAPI_Test | Test / mock | — (test code, no migration action)
ConfigsPickList | Class | 8. Not Migrating
ConfigsPickListTest | Test / mock | — (test code, no migration action)
EncryptionUtil | Class | 8. Not Migrating
EncryptionUtil_Test | Test / mock | — (test code, no migration action)
ExportReportToJSONController | Aura/LWC controller | 8. Not Migrating
ExportReportToJSONControllerTest | Test / mock | — (test code, no migration action)
FieldData | Class | 8. Not Migrating
FieldDataTest | Test / mock | — (test code, no migration action)
FieldDef | Class | 8. Not Migrating
FieldDefTest | Test / mock | — (test code, no migration action)
FieldPickerController | Aura/LWC controller | 8. Not Migrating
FieldPickerController_Test | Test / mock | — (test code, no migration action)
FixSOTransactionsBatch | Batch | 8. Not Migrating
FlowEmailComposerCtrl | Aura/LWC controller | 8. Not Migrating
FlowEmailComposerCtrlTest | Test / mock | — (test code, no migration action)
ForgotPasswordController | Class | 8. Not Migrating
ForgotPasswordControllerTest | Test / mock | — (test code, no migration action)
LightningForgotPasswordController | Aura/LWC controller | 8. Not Migrating
LightningForgotPasswordControllerTest | Test / mock | — (test code, no migration action)
LightningLoginFormController | Aura/LWC controller | 8. Not Migrating
LightningLoginFormControllerTest | Test / mock | — (test code, no migration action)
LightningSelfRegisterController | Aura/LWC controller | 8. Not Migrating
LightningSelfRegisterControllerTest | Test / mock | — (test code, no migration action)
MicrobatchSelfRegController | Class | 8. Not Migrating
MicrobatchSelfRegControllerTest | Test / mock | — (test code, no migration action)
MultiRequestMock | Test / mock | — (test code, no migration action)
MyProfilePageController | Class | 8. Not Migrating
MyProfilePageControllerTest | Test / mock | — (test code, no migration action)
QuickLightningLookupController | Aura/LWC controller | 8. Not Migrating
QuickLightningLookupControllerTest | Test / mock | — (test code, no migration action)
SendBetterEmail | Invocable | 8. Not Migrating
SendBetterEmailAddAttachmentToEmail | Class | 8. Not Migrating
SendBetterEmailAddTasksToEmail | Class | 8. Not Migrating
SendBetterEmailBulk | Invocable | 8. Not Migrating
SendBetterEmailBulkRequestSetup | Invocable | 8. Not Migrating
SendBetterEmailConstant | Class | 8. Not Migrating
SendBetterEmailRequest | Aura/LWC controller | 8. Not Migrating
SendBetterEmailResponse | Aura/LWC controller | 8. Not Migrating
SendBetterEmailTest | Test / mock | — (test code, no migration action)
SendBetterEmailUtil | Class | 8. Not Migrating
SingleRequestMock | Test / mock | — (test code, no migration action)
SiteLoginController | Class | 8. Not Migrating
SiteLoginControllerTest | Test / mock | — (test code, no migration action)
SiteRegisterController | Class | 8. Not Migrating
SiteRegisterControllerTest | Test / mock | — (test code, no migration action)
TabularReportResponse | Class | 8. Not Migrating
TabularReportResponseTest | Test / mock | — (test code, no migration action)
TestFixSOTransactionsBatch | Test / mock | — (test code, no migration action)
ZEN_APIHandler | Class | 4.5 Portal & Website APIs
ZEN_Batch_UpdateFinanceExport | Batch | 5. Payments, Finance & DD
ZEN_CheckoutRedirect | Aura/LWC controller | 5. Payments, Finance & DD
ZEN_CheckoutRedirectTest | Test / mock | — (test code, no migration action)
ZEN_FinanceExport | Aura/LWC controller | 5. Payments, Finance & DD
ZEN_FinanceExportTest | Test / mock | — (test code, no migration action)
ZEN_JSAP_Controller | Aura/LWC controller | 4.5 Portal & Website APIs
ZEN_JSAP_ControllerTest | Test / mock | — (test code, no migration action)
ZEN_Register_Redirect | Aura/LWC controller | 4.5 Portal & Website APIs
ZEN_Register_Redirect_test | Test / mock | — (test code, no migration action)
ZEN_ws_CPDPoints | REST API | 4.5 Portal & Website APIs
ZEN_ws_CPDPoints_Test | Test / mock | — (test code, no migration action)
ZEN_ws_ChangePassword | REST API | 4.5 Portal & Website APIs
ZEN_ws_ChangePassword_Test | Test / mock | — (test code, no migration action)
ZEN_ws_CreateCase | REST API | 4.5 Portal & Website APIs
ZEN_ws_CreateCase_Test | Test / mock | — (test code, no migration action)
ZEN_ws_Preferences | REST API | 4.5 Portal & Website APIs
ZEN_ws_Preferences_Test | Test / mock | — (test code, no migration action)
ZEN_ws_checkMemberStatus | REST API | 4.5 Portal & Website APIs
ZEN_ws_checkMemberStatus_Test | Test / mock | — (test code, no migration action)
ZEN_ws_getFormulary | REST API | 4.5 Portal & Website APIs
ZEN_ws_getFormulary_Test | Test / mock | — (test code, no migration action)
ZEN_ws_getebook | REST API | 4.5 Portal & Website APIs
ZEN_ws_getebook_Test | Test / mock | — (test code, no migration action)
ZEN_ws_myAddresses | REST API | 4.5 Portal & Website APIs
ZEN_ws_myAddresses_Test | Test / mock | — (test code, no migration action)
ZEN_ws_mydetails | REST API | 4.5 Portal & Website APIs
ZEN_ws_mydetails_Test | Test / mock | — (test code, no migration action)
Zen_GuidUtil | Class | 8. Not Migrating
Zen_GuidUtilTest | Test / mock | — (test code, no migration action)
Zen_IntAcct_APICall | Class | 5. Payments, Finance & DD
Zen_IntAcct_APICallTest | Test / mock | — (test code, no migration action)
Zen_LoginFlowController | Class | 4.5 Portal & Website APIs
Zen_LoginFlowControllerTest | Test / mock | — (test code, no migration action)
Zen_SOL_CalculateRollupsTest | Test / mock | — (test code, no migration action)
Zen_XMLParser | Class | 5. Payments, Finance & DD
Zen_XMLParser_TEST | Test / mock | — (test code, no migration action)
Zen_flowaction_PostTransactions | Invocable | 5. Payments, Finance & DD
Zen_flowaction_PostTransactionsTest | Test / mock | — (test code, no migration action)
Zen_redirectDDCookieController | Class | 5. Payments, Finance & DD
Zen_redirectDDCookieControllerTest | Test / mock | — (test code, no migration action)
batchFlowSendEmail | Batch | 6. Events, CPD & LMS
dlrs_EventApi_SpeakerTest | Test / mock | — (test code, no migration action)
dlrs_LTE_Site_EventTest | Test / mock | — (test code, no migration action)
dlrs_OrderApi_Catalog_ItemTest | Test / mock | — (test code, no migration action)
dlrs_OrderApi_Receipt_LineTest | Test / mock | — (test code, no migration action)
dlrs_OrderApi_Sales_Order_LineTest | Test / mock | — (test code, no migration action)
dlrs_Zen_Committee_MembershipTest | Test / mock | — (test code, no migration action)
ers_DatatableController | Aura/LWC controller | 8. Not Migrating
ers_DatatableControllerTest | Test / mock | — (test code, no migration action)
ers_EncodeDecodeURL | Invocable | 8. Not Migrating
ers_EncodeDecodeURLTest | Test / mock | — (test code, no migration action)
ers_QueryNRecords | Invocable | 8. Not Migrating
ers_QueryNRecordsTest | Test / mock | — (test code, no migration action)
pdfConfigController | Aura/LWC controller | 8. Not Migrating
pdfConfigControllerTest | Test / mock | — (test code, no migration action)
pdfGeneratorController | Aura/LWC controller | 8. Not Migrating
pdfGeneratorController_Test | Test / mock | — (test code, no migration action)
picklist_Controller | Aura/LWC controller | 8. Not Migrating
picklist_Controller_Test | Test / mock | — (test code, no migration action)
sObjectUtils | Class | 8. Not Migrating
viewzController | Aura/LWC controller | 8. Not Migrating
viewzController_Test | Test / mock | — (test code, no migration action)
zenDataTableController | Aura/LWC controller | 8. Not Migrating
zenDataTableController_Test | Test / mock | — (test code, no migration action)
zenFormField | Aura/LWC controller | 8. Not Migrating
zenMemberLinkController | Aura/LWC controller | 8. Not Migrating
zenMemberLinkControllerTest | Test / mock | — (test code, no migration action)
zenRecordFormController | Aura/LWC controller | 8. Not Migrating
zenRecordFormControllerTest | Test / mock | — (test code, no migration action)
zen_BatchUpdateUserBadges | Batch | 4.4 Entitlements & SSO
zen_BatchUpdateUserBadgesTest | Test / mock | — (test code, no migration action)
zen_BatchUpdateUserPrimaryRole | Batch | 4.6 Contact-User Hygiene
zen_BatchUpdateUserPrimaryRoleTest | Test / mock | — (test code, no migration action)
zen_Batch_DeleteRecords | Batch | 5. Payments, Finance & DD
zen_Batch_DeleteSchPaymentRecords | Batch | 5. Payments, Finance & DD
zen_FlowAction_Delete | Invocable | 5. Payments, Finance & DD
zen_FlowAction_Delete_Test | Test / mock | — (test code, no migration action)
zen_FlowAction_FindDuplicates | Invocable | 5. Payments, Finance & DD
zen_FlowAction_FindDuplicates_Test | Test / mock | — (test code, no migration action)
zen_FlowAction_FindSchDuplicates | Invocable | 5. Payments, Finance & DD
zen_FlowAction_FindSchDuplicatesTest | Test / mock | — (test code, no migration action)
zen_FlowAction_SchPayDeleteTest | Test / mock | — (test code, no migration action)
zen_FlowAction_SchPaymentDelete | Invocable | 5. Payments, Finance & DD
zen_MoodleCourseCompletionStatus | Class | 6. Events, CPD & LMS
zen_MoodleCourseCompletionStatus_Test | Test / mock | — (test code, no migration action)
zen_MoodleCourses | Class | 6. Events, CPD & LMS
zen_MoodleEnrolCourse | Invocable | 6. Events, CPD & LMS
zen_MoodleEnrolCourseTest | Test / mock | — (test code, no migration action)
zen_MoodleUserDetails | Class | 6. Events, CPD & LMS
zen_MoodleUserDetails_Test | Test / mock | — (test code, no migration action)
zen_SageFinanceExport | Batch | 5. Payments, Finance & DD
zen_SageFinanceExportTest | Test / mock | — (test code, no migration action)
zen_ScheduleMoodleCourses | Schedulable | 6. Events, CPD & LMS
zen_ScheduleMoodleCoursesTest | Test / mock | — (test code, no migration action)
zen_SchedulePostTransactions | Schedulable | 5. Payments, Finance & DD
zen_SchedulePostTransactionsTest | Test / mock | — (test code, no migration action)
zen_flowActionPostSalesOrder | Invocable | 5. Payments, Finance & DD
zen_flowActionPostSalesOrderTest | Test / mock | — (test code, no migration action)
zen_flowaction_SageExport | Invocable | 5. Payments, Finance & DD
zen_flowaction_SageExportTest | Test / mock | — (test code, no migration action)
zen_ws_getuserdetails | REST API | 4.5 Portal & Website APIs
zen_ws_getuserdetailsTest | Test / mock | — (test code, no migration action)
zen_ws_memberstatus | REST API | 4.5 Portal & Website APIs
zen_ws_memberstatusTest | Test / mock | — (test code, no migration action)